## Risk Matrix
⚠ HAZARD ASSESSMENT RISK MATRIX
WorkSafe Sounds ¦ Ontario Construction Industry ¦ OHSA Compliant
RISK LEVEL LEGEND
LOW | Score 1–4 | Acceptable risk. Monitor and maintain controls.
MEDIUM | Score 5–9 | Moderate risk. Implement controls within 30 days.
HIGH | Score 10–14 | Significant risk. Immediate corrective action required.
CRITICAL | Score 15–25 | Unacceptable risk. Stop work. Immediate action mandatory.
RISK MATRIX (Likelihood × Severity)
| S1 Negligible | S2 Minor | S3 Moderate | S4 Major | S5 Catastrophic
LIKELIHOOD ↑ | 5 MED | 10 HIGH | 15 CRIT | 20 CRIT | 25 CRIT
| 4 LOW | 8 MED | 12 HIGH | 16 CRIT | 20 CRIT
| 3 LOW | 6 MED | 9 MED | 12 HIGH | 15 CRIT
| 2 LOW | 4 LOW | 6 MED | 8 MED | 10 HIGH
| 1 LOW | 2 LOW | 3 LOW | 4 LOW | 5 MED

## Hazard Log
⚠ HAZARD IDENTIFICATION & RISK ASSESSMENT LOG
WorkSafe Sounds ¦ Ontario Construction ¦ OHSA S.25(2)(h)
Project / Site: |  | Supervisor: |  | Date: |  | Review Date:
Ref # | Hazard Description | Location / Task | Exposed Workers | Existing Controls | Likelihood (1–5) | Severity (1–5) | Risk Score (L × S) | Risk Level | Recommended Actions | Responsible Person | Target Date | Completion Date | Status
001 | Working at heights – unguarded edge | Floor 3 framing | Carpenters, Ironworkers | Safety harness, lanyards, anchor points | 3 | 5 | 15 | CRITICAL | Install lifeline system; daily harness inspection | Site Supervisor | 2026-03-01 |  | Open
002 | Struck-by – swinging crane load | Crane pick zone | All trades in radius | Exclusion zone, signaller, tag lines | 2 | 5 | 10 | HIGH | Establish crane exclusion zone markers; signaller required at all times | Crane Operator / Supervisor | Ongoing |  | Open
003 | Electrical – live panel exposure | Electrical room B | Electricians | LOTO procedure, rubber gloves | 2 | 4 | 8 | MEDIUM | Verify LOTO compliance before any panel work; daily inspection | Master Electrician | 2026-02-28 |  | Open
004 | Slip/trip – slippery walking surface | Wet concrete slab | All workers | Anti-slip mats, housekeeping schedule | 4 | 2 | 8 | MEDIUM | Increase cleaning frequency; add grit strips in high-traffic zones | Safety Officer | Ongoing |  | Open
005 | Chemical – silica dust exposure | Concrete cutting area | Labourers | Wet cutting method, N95 respirator | 2 | 1 | 2 | LOW | Upgrade to P100 respirator; air monitoring monthly | Safety Officer | 2026-03-15 |  | Open
006
007
008
009
010
011
012
013
014
015
016
This document must be reviewed and signed by the Health & Safety Representative before work commences. Retain for minimum 3 years per OHSA requirements.

## Scales Reference
LIKELIHOOD & SEVERITY SCALES — REFERENCE GUIDE
LIKELIHOOD SCALE
Rating | Level | Description | Frequency | Example | Ontario Context
1 | Rare | Could occur only in exceptional circumstances | Less than once per 10 years | First-ever incident on site | No incidents in company history
2 | Unlikely | Could occur but not expected | Once per 3–10 years | Isolated near-miss report | Rare sector-wide occurrence
3 | Possible | Could occur at some time | Once per 1–3 years | Has occurred on similar sites | Documented in WSIB sector data
4 | Likely | Will probably occur in most circumstances | Once per 6–12 months | Recurring near-misses | Common across Ontario construction
5 | Almost Certain | Expected to occur in most circumstances | Monthly or more frequent | Regular occurrence without controls | High WSIB claim frequency in sector
SEVERITY SCALE
Rating | Level | Description | Frequency | Example | Ontario Context
1 | Negligible | Minimal health/safety impact | First aid only; no lost time | Minor cut requiring bandage | No WSIB reportable incident
2 | Minor | Some injury; short recovery | Medical aid; <1 week lost time | Sprain requiring physiotherapy | WSIB Type 1 claim; RTW same week
3 | Moderate | Moderate injury; significant recovery | 1–4 weeks lost time | Fracture requiring surgery | WSIB Lost Time Injury (LTI)
4 | Major | Severe injury; long-term impact | >4 weeks; possible permanent impairment | Crush injury, severe burns, TBI | Critical injury — MOL notification required
5 | Catastrophic | Death or permanent total disability | Fatality or permanent total disability | Fall from height fatality | MOL fatality investigation; coroner inquest